## Sheet1
| Keisha | Bradley | Anna | Josie | Harry | Richard | Callum | Zoe | Osman
Steam Handling | I | I | R | C | I | A | I | I | I
Steam Intergration |  | C | A | R | I |  | I |  | A
Social Media | I: R; I: I; C: C; I: A | R - Responsible | The individual who executes the task.
Social Maintainence | I: R; I: A; C: C; I: A | A - Accountable | The person who signs off on the task and ensures it meets quality standards.
Documentation | A | R | I | I | I | I | C | I | I | C - Consulted | The person who provides input and feedback before the task is completed.
Reviewing Pushes | I | I |  | C | A |  | R |  | I | I - Informed | The person who is kept updated on the progress and outcomes of the task.
Ticket Maintainence | R: I; I: A; I: C; I: R
Ticket Reviewing | I | A | C | I | R | A | A | C | A
Figma | R | A | C | I | I | I | I | I | I
Clickup | R | A | I | C | I | I | A | I | I
Public Discord | A | C |  | C |  | A |  | R
Steamdeck |  | I | R | A | A | I | C |  | I
Audio Intergration | I |  | A | A |  |  |  | R | A
QA Testing | A | C | R | I | I | R | C | A | I
Multiplayer |  | A | I | R | R |  | A |  | C
Automated Builds | I | A | I | A | A | I | R | I | I
Art Liason | bar: A to I
Animaton Liason | bar: A to I
Design Liason | C: A; I: C; C: R; I: R
Art Intergration | bar: A to I
Gameplay | C | A | C | C | R | C | C | C | A
HR | bar: A to I
Git Management | I | A | I | I | R | C | A | I | I
| R | A | C | I |  | TOTAL
Keisha | A I: 4; R A: 4; R I: 1; R I: 6; R C: 14
Bradley | A I: 2; R A: 9; R I: 3; R I: 5; R C: 18
Anna | A I: 3; R A: 2; R I: 3; R I: 5; R C: 12
Josie | A I: 4; R A: 4; R I: 7; R I: 5; R C: 19
Harry | A I: 4; R A: 3; R I: 2; R I: 6; R C: 14
Richard | A I: 1; R A: 3; R I: 1; R I: 4; R C: 9
Callum | A I: 4; R A: 3; R I: 5; R I: 3; R C: 14
Zoe | A I: 4; R A: 3; R I: 1; R I: 6; R C: 13
Osman | A I: 2; R A: 4; R I: 1; R I: 9; R C: 15